SCOPE OF WORK

CANTON

INTELLIGENCE

DASHBOARD

FLOWRYD CONTROL CENTRE

Interactive Participant Map & Live Intelligence Feed

| CLIENT Liz Towler Flowryd | DELIVERY 3–5 Days From kick-off | TASKS 8 Tasks 4 Waves | INVESTMENT $4,500 Single milestone |
| --- | --- | --- | --- |

PREPARED BY WILLIAM LEE  /  FEBRUARY 28, 2026

# EXECUTIVE SUMMARY

This document outlines the scope, deliverables, and timeline for building the Canton Intelligence Dashboard within Flowryd’s existing Control Centre. The dashboard will provide a real-time, interactive view of the Canton Network ecosystem—mapping 80+ participant organisations geographically and surfacing relevant industry news in a unified intelligence feed.

The dashboard is designed as a strategic decision-support tool, giving Flowryd’s team and stakeholders an instant visual understanding of the network’s global reach, participant concentration by region, and the latest developments shaping the Canton ecosystem.

This project builds directly on the existing Control Centre codebase delivered in our previous engagement ($15,000 USD), ensuring zero ramp-up time, full architectural consistency, and immediate integration.

# THE PROBLEM

The Canton Network has grown to over 80 participants globally, but there is no centralised, visual way to understand the scope, geography, or evolution of this network.

- Participant data is scattered across documentation, spreadsheets, and announcements with no unified view

- No geographic visualisation showing where participants are concentrated or where gaps exist

- Industry news and developments are spread across dozens of sources with no aggregation

- Stakeholders lack a single dashboard to assess network health and trajectory at a glance

# THE SOLUTION

## Interactive World Map

A dark-themed, WebGL-accelerated world map displaying every Canton Network participant as an interactive marker.

- 82 participant locations with precise coordinates

- Clickable markers revealing: name, type, region, Canton role

- Cluster aggregation for dense regions

- Smooth zoom, pan, and rotation with globe-to-flat transitions

- Region filtering: Americas, EMEA, APAC

- Responsive across all screen sizes

## Live Intelligence Feed

Real-time news panel aggregating Canton Network and enterprise blockchain news.

- Primary: CryptoPanic API for curated blockchain news

- Fallback: RSS aggregation from key industry publications

- Server-side /api/intel/news route with 5-minute caching

- News cards: headline, source, timestamp, relevance tag, thumbnail

- Auto-refresh with manual override

- Category filtering: Canton, DeFi, enterprise, regulatory

## Dashboard Composition

- Full-width map with collapsible right-side news panel

- Dashboard header with network stats: participants, regions, last update

- Integrated into Control Centre sidebar (INTEL tier)

- Dark theme matching existing design language

- Full keyboard accessibility

# TECHNICAL ARCHITECTURE

| Component | Technology | Rationale |
| --- | --- | --- |
| Map Renderer | react-map-gl + maplibre-gl | MIT licensed, WebGL, production-grade |
| Tiles | CartoDB Dark Matter | Free, dark theme, no API key needed |
| News API | CryptoPanic API | Curated crypto/blockchain feed |
| Fallback | RSS aggregation | Zero-dependency backup |
| Data | Static TypeScript file | No DB changes. Versioned JSON. |
| API Route | Next.js /api/intel/news | Server-side, cached, no CORS |
| State | Existing patterns | Consistent with codebase |

# TASK BREAKDOWN

8 tasks across 4 execution waves. Waves 1 and 2 are parallelisable.

## Wave 1 / Foundation

| ID | Task | Deliverable |
| --- | --- | --- |
| ID01 | Install react-map-gl + maplibre-gl. Configure bundler. Verify WebGL in build pipeline. | Dependencies installed, map renders in dev |
| ID02 | Compile lat/lng for 82 Canton participants. Create typed data file. | canton-participants.ts with 82 entries |
| ID03 | Wire INTEL tier into sidebar. Add route in FlowsStudio. Configure feature flag. | INTEL tab visible, routes to dashboard |
| ID04 | Build /api/intel/news. Integrate CryptoPanic + RSS fallback. Add caching. | API endpoint returning formatted news |

## Wave 2 / Core Components

| ID | Task | Deliverable |
| --- | --- | --- |
| ID05 | Build IntelMap.tsx. Dark map, markers, click popups, clustering, region filters. | Interactive map with all features |
| ID06 | Build IntelNewsFeed.tsx. Consume API, render cards, auto-refresh, filtering. | News feed panel with live data |

## Wave 3 / Composition

| ID | Task | Deliverable |
| --- | --- | --- |
| ID07 | Build IntelligenceDashboard.tsx. Compose map + news. Header stats. Collapsible panel. Responsive. | Complete dashboard in Control Centre |

## Wave 4 / Polish & QA

| ID | Task | Deliverable |
| --- | --- | --- |
| ID08 | Visual polish. Accessibility audit. Cross-browser testing. Production build verification. | Production-ready, all QA passed |

# TIMELINE

| DAY | WAVE | WORK | GATE |
| --- | --- | --- | --- |
| Day 1 | Wave 1 | Dependencies, data, sidebar, API | Foundation complete |
| Day 2 | Wave 2 | Map + News feed built in parallel | Components render with data |
| Day 3 | Wave 3 | Dashboard composition + integration | Full dashboard functional |
| Day 4 | Wave 4 | Polish, accessibility, QA | All checks passed |
| Day 5 | Delivery | Production build + deployment | Live in production |

# INCLUDED

- Interactive WebGL world map with 82 participant locations

- Clickable markers with detail popups

- Cluster aggregation for dense regions

- Region-based filtering (Americas, EMEA, APAC)

- Live news feed from CryptoPanic + RSS fallback

- News cards with headline, source, timestamp, thumbnail

- Server-side API route with caching

- Auto-refresh and manual refresh

- Category-based news filtering

- Collapsible news panel for full-screen map

- Dashboard header with network statistics

- Full Control Centre sidebar integration

- Dark theme matching existing UI

- Responsive design (desktop, tablet, mobile)

- Keyboard accessibility + ARIA compliance

- Cross-browser testing

- Production build with zero warnings

- One commit per wave

# NOT INCLUDED

- Database schema changes or migrations

- Authentication changes or new permission roles

- Real-time WebSocket connections

- Custom map tile hosting

- Historical news archiving or search

- Participant data entry UI

- Mobile native app development

- Ongoing maintenance post-delivery

# OPEN DECISIONS

| # | Decision | Recommended | Alternative |
| --- | --- | --- | --- |
| 1 | Sidebar icon for INTEL tier | Radar icon | Globe or custom Canton icon |
| 2 | News panel position | Right-side overlay (collapsible) | Bottom panel or tab |
| 3 | CryptoPanic API key | Flowryd provides key | RSS-only (free, fewer sources) |
| 4 | Commit strategy | One commit per wave | Feature branch + squash |

# INVESTMENT

| PROJECT FEE | $4,500 USD |
| --- | --- |
| PAYMENT | 50% upfront / 50% on delivery |
| DELIVERY | 3–5 business days from kick-off |
| START | Immediate upon deposit |

Pricing reflects efficiency from existing familiarity with the Flowryd codebase, eliminating onboarding overhead.

# NEXT STEPS

- Review and approve this scope of work

- Confirm the 4 open decisions

- Provide CryptoPanic API key (if using primary source)

- Confirm deposit to initiate

- Kick-off: Wave 1 begins immediately

BUILT ON WHAT WE’VE ALREADY DELIVERED.

READY TO START IMMEDIATELY.

WILLIAM LEE  /  FULL-STACK DEVELOPER

PREVIOUS: FLOWRYD CONTROL CENTRE  /  $15,000 USD