SCOPE OF WORK

Flowryd M3

Canton Network Integration

Live Ledger • $CC Settlement • Institutional Custody

Prepared for

Liz Towler  —  Flowryd

Prepared by

William Lee  —  Full-Stack Engineer

February 28, 2026

| Objective | Every Submit button triggers a real Canton cryptographic event with $CC settlement |
| --- | --- |
| Frontend Changes | Zero. Backend swap only. |
| Calendar Timeline | 12–16 weeks (3–4 months) |
| Engineering Cost | $85K–$115K (AI-accelerated) |
| Total Year 1 Cost | $395K–$825K (incl. vendors) |
| Biggest Risk | IEU/Daml contract delivery |
| Quick Win | Partner portal ships Week 1, no vendor deps |

# Executive Summary

This document is the complete Milestone 3 scope of work for Flowryd. M3 takes the existing Control Centre — 57 API routes, 20+ database tables, 80+ participant profiles, all built and deployed in M2 — and wires it to the live Canton Network with real cryptographic settlement.

The goal is simple: every action in Flowryd that currently writes to PostgreSQL will also execute a real Daml smart contract on Canton. Every deal that closes will settle real $CC (Canton Coin) through Fireblocks institutional-grade custody. Zero frontend changes. The entire UI stays the same. This is a backend swap.

The work is split into two parallel lanes: Will’s engineering lane (code, architecture, integration) and Liz’s partnerships lane (vendor agreements, licensing, coordination). Both lanes must move simultaneously — engineering is blocked at multiple points by vendor access that only Liz can unlock.

# How to Read This Document

WILL’S LANE — Code, architecture, integration. AI-accelerated. Will builds with AI tooling, moves fast.

LIZ’S LANE — Vendor agreements, partnerships, licensing. Human-to-human. Cannot be automated.

Every work item is tagged with an owner. If it says BLOCKED BY LIZ, Will literally cannot start until Liz delivers the vendor access or agreement.

# The Two Lanes — Overview

| Week | Will’s Lane (Engineering) | Liz’s Lane (Partnerships) |
| --- | --- | --- |
| 1 | Partner onboarding portal | IEU partnership (CRITICAL) |
| 2 | Node config + proxy wiring | Fireblocks enterprise agreement |
| 3 | Party-ID ledger verification | 5North engagement (KYC) |
| 4 | LiveCantonService scaffold | 7Trust engagement (DNS verify) |
| 5–6 | BLOCKED — waiting on Daml contracts from IEU | Whitepaper V1 with IEU |
| 7 | LiveCantonService goes live | Partner outreach (first 10) |
| 8 | Ledger sync + dual-write | Continue outreach |
| 9 | $CC / Fireblocks wiring | TRM Labs / Chainlink APIs |
| 10 | CPM integration | Continue vendor onboarding |
| 11 | Partner adapter patterns | Security audit scheduling |
| 12 | E2E testing on testnet | Coordinate DA/IEU review |
| 13–14 | Dual-write soak period | Security audit execution |
| 15 | Staged rollout (internal) | Internal QA sign-off |
| 16 | Staged rollout (partners) | GO LIVE |

# Liz’s Lane — Vendor Requirements

Everything Liz needs to secure, ordered by urgency. Without these vendor agreements, engineering stalls at clearly marked blocking points.

## Priority 1: IntellectEU (IEU) / Catalyst Partnership

BLOCKS EVERYTHING. IEU provides the Canton validator node, writes the Daml smart contracts, and packages everything via CPM. Without IEU, there is no M3.

| Requirement | Why | When |
| --- | --- | --- |
| Signed partnership | Legal foundation for entire M3 | Week 1 |
| Testnet validator node | Confirm canton.test.catalyst.flowryd.xyz is ours | Week 1 |
| Mainnet validator node | Production environment | Week 12 |
| Daml contract development | 12 role templates + 5 adapter patterns + core workflow contracts | Weeks 3–8 |
| Catalyst CBM + CPM license | Infrastructure management + package deployment | Week 1 |
| Whitepaper tech section | IEU writes app stack architecture section | Weeks 4–6 |
| Ongoing node hosting (K8s) | 2 nodes: test + production | Ongoing |

Estimated Cost:

| Line Item | Cost |
| --- | --- |
| Catalyst license (CBM + CPM) | $50K–$100K/year |
| Node hosting (2 nodes) | $6K–$10K/month ($72K–$120K/year) |
| Daml contract development + consulting | $80K–$150K one-time |
| IEU Total Year 1 | $200K–$370K |

Negotiation leverage: Flowryd is a showcase customer for Canton Network. IEU gets a reference customer deploying Catalyst in production. This should drive pricing down.

## Priority 1: Fireblocks — $CC Custody & Settlement

CRITICAL. Real $CC (Canton Coin) must flow through institutional-grade custody. Fireblocks is the standard.

| Requirement | Why | When |
| --- | --- | --- |
| Enterprise API access | Vault management, transfer API, policy engine | Week 6 (sandbox Week 2) |
| Canton External Signing | Fireblocks signs Daml transactions via MPC keys | Week 8 |
| Sandbox environment | Development against test $CC | Week 2 |
| Solution engineering | UTXO ($CC Splice Amulet) integration is non-trivial | Weeks 8–10 |

Key technical context: $CC uses a UTXO model (like Bitcoin, not Ethereum). Fireblocks doesn’t have a native Canton driver — they integrate via External Signing where Fireblocks holds private keys and signs Canton transactions remotely. This requires their solution engineering team, not just API access.

Estimated Cost:

| Line Item | Cost |
| --- | --- |
| Fireblocks enterprise license | $50K–$100K/year |
| Fireblocks Total Year 1 | $50K–$100K |

## Priority 2: 5North (KYC) & 7Trust (DNS Verification)

Needed by Week 3–4. Canton-native identity verification services.

| Vendor | Purpose | Ask | Cost |
| --- | --- | --- | --- |
| 5North | Canton-native KYC. Verifies Party ID = real KYC’d company | API access + sandbox | TBD (partnership) |
| 7Trust (7Ridge) | DNS verification. Proves Party ID = specific domain | API for PartyID ↔ DNS proof | TBD (partnership) |

## Priority 3: Partner APIs (Adapter Tier)

Needed by Week 10–12. Off-chain services that Daml contracts talk to. Will builds the adapter pattern first, then wires specific vendor APIs.

| Vendor | Purpose | Cost/Month | When |
| --- | --- | --- | --- |
| Chainlink / Pyth | Real-time price feeds for collateral | $1K–$3K | Week 12 |
| TRM Labs / Elliptic | Pre-trade AML/sanctions screening | $2K–$5K | Week 12 |
| Chainalysis | Ongoing transaction monitoring | $2K–$5K | Week 14 |
| Noves | Human-readable deal history | $500–$2K | Week 14 |
| ALUM Labs | Validator network health telemetry | $500–$1K | Week 14 |
| Total |  | $6K–$16K/mo |  |

Minimum for launch: Chainlink/Pyth + TRM Labs = ~$3K–$8K/month. Others can be phased in post-launch.

## Priority 4: Security Audits

| What | Who | When | Cost |
| --- | --- | --- | --- |
| Daml contract security review | IEU/Digital Asset (may be included in V1) | Week 14 | $15K–$30K |
| API penetration test | Third-party security firm | Week 14 | $10K–$20K |
| Total |  |  | $25K–$50K |

# Vendor Cost Summary

| Vendor | One-Time | Year 1 Recurring | Total Year 1 | Priority |
| --- | --- | --- | --- | --- |
| IEU / Catalyst | $80K–$150K | $122K–$220K | $200K–$370K | P1 — ASAP |
| Fireblocks | — | $50K–$100K | $50K–$100K | P1 — Wk 2 |
| 5North | — | TBD | TBD | P2 — Wk 3 |
| 7Trust | — | TBD | TBD | P2 — Wk 3 |
| Partner APIs | — | $36K–$96K | $36K–$96K | P3 — Wk 12 |
| Security Audits | $25K–$50K | — | $25K–$50K | P4 — Wk 14 |
| TOTAL VENDOR | $105K–$200K | $208K–$416K | $310K–$615K |  |

# Will’s Lane — Engineering Work Plan

All timelines assume AI-assisted development. What used to be 3 weeks of coding becomes 1 week. Will works with AI tooling and moves fast.

## W1: Participant Onboarding Portal

SHIPS WEEK 1. Zero vendor dependency. Can start immediately. Liz can begin inviting partners to claim profiles this week.

| Task | Detail | Time |
| --- | --- | --- |
| Seed participants DB | Load 80+ companies from canton-data.ts into participants table | 2 hours |
| Onboarding wizard | /onboard page — company connects, matches profile, claims it | 1–2 days |
| Claim API | POST /api/participants/[id]/claim — wire logic | 0.5 day |
| Admin review | Admin panel → Participants tab → approve/reject claims | 0.5 day |
| Discover reads from DB | Swap static import to database query | 0.5 day |
| Total |  | ~3 days |

## W2: Canton Node Configuration

BLOCKED BY: Liz → IEU confirms test node, provides Participant ID

| Task | Detail | Time |
| --- | --- | --- |
| Wire admin UI to CBM | Update node_api_configs with live CBM endpoint | 0.5 day |
| Test Ledger API proxy | Verify /api/node-api/proxy hits /participants/{name}/jsonapi/v2/query | 0.5 day |
| JWT auth for Ledger API | Generate Canton JWTs with actAs/readAs party claims | 1 day |
| Total |  | ~2 days |

## W3–4: Identity Verification

BLOCKED BY: Liz → 5North + 7Trust API access

| Task | Detail | Time |
| --- | --- | --- |
| Canton topology queries | DumpParticipantIdentities — verify Party IDs on-ledger | 1 day |
| ANS integration | Resolve human-readable names to Party IDs via Splice.Ans | 1 day |
| Update validate-party-id.ts | Add async verifyOnLedger() — regex + ledger authority | 0.5 day |
| 5North KYC integration | Wire 5N ID API for participant KYC status | 1–2 days |
| 7Trust DNS verification | PartyID ↔ domain proof | 1 day |
| Verification badges UI | Shield icon (KYC), checkmark (DNS) in Discover | 0.5 day |
| Total |  | ~5–6 days |

## W4–5: LiveCantonService Scaffold

Requires test node from W2. Does NOT require Daml contracts yet — builds against mock contracts initially.

| Task | Detail | Time |
| --- | --- | --- |
| Install @daml/ledger SDK | Add TypeScript Daml client packages | 1 hour |
| Create live.ts | LiveCantonService implements CantonService — all 5 methods | 1–2 days |
| Ledger client wrapper | Auth-aware @daml/ledger wrapper with token refresh | 0.5 day |
| Environment factory | CANTON_MODE=mock¦live toggle in index.ts | 1 hour |
| Total |  | ~3 days |

## W5–7: Pre-Build Phase (While Waiting on IEU)

BLOCKED on IEU Daml contract delivery. Will is not idle — pre-builds everything possible:

- Onboarding wizard improvements based on first partner feedback

- Intelligence Dashboard enhancements

- Fireblocks client library (against sandbox)

- Adapter pattern scaffolds (oracle, compliance gate)

- Integration tests against mock contracts

What IEU needs to deliver (Will provides the exact spec):

| PostgreSQL Table | Daml Template | Choices Needed |
| --- | --- | --- |
| deals + deal_status | DealStateMachine | OpenDeal, StartNegotiation, LockDeal, CommitDeal, ResetToDraft |
| deal_participants | DealParticipantAgreement | SignOff, Withdraw |
| flows | FlowWorkflow | Publish, Archive, AddParticipant |
| payment_methods + invoices | CCTransfer + OrchestratorFee | InitiateTransfer, ConfirmSettlement, DistributeFees |
| FA marker concept | FAMarkerReward | AccumulateMarkers, DistributeRewards |
| 12 role categories | 12 Role Templates | InstallRole, ActivateRole, DeactivateRole |

This is not ambiguous. Will specifies every field, every choice, every state transition. IEU translates to Daml syntax and handles Canton-specific patterns (privacy, authorization, sub-transactions).

## W7–8: LiveCantonService Goes Live

BLOCKED BY: IEU delivers Daml contracts

| Task | Detail | Time |
| --- | --- | --- |
| Wire real contracts | Point deployContract() at real DAR templates | 1 day |
| Wire state machine | Deal status changes → Daml exercise commands | 1 day |
| Ledger event subscription | Canton transaction stream → auto-update PostgreSQL mirror | 2 days |
| Dual-write mode | Write to Daml + PostgreSQL. Read from PostgreSQL. Reconciliation. | 1 day |
| Total |  | ~5 days |

## W9–10: $CC Settlement

BLOCKED BY: Liz → Fireblocks sandbox access

| Task | Detail | Time |
| --- | --- | --- |
| Fireblocks client library | Vault management, transfer API, policy engine wrapper | 1 day |
| Topology onboarding | Register Fireblocks keys on Canton (with IEU help) | 2 days |
| Splice External Party setup | createExternalPartySetupProposal on AmuletRules | 1 day |
| Settlement bridge | Listen for Daml signature requests → forward to Fireblocks | 2 days |
| Atomic settlement | Deal committed → auto $CC transfer with fee split | 1 day |
| Payment history UI | $CC transaction history in deal rooms | 0.5 day |
| Total |  | ~7–8 days |

## W10–11: CPM Packaging & Partner Adapters

| Task | Detail | Time |
| --- | --- | --- |
| CPM integration API | Check package status, trigger installs via Catalyst CPM | 2 days |
| Wire Jumpstarts to CPM | Template selection → CPM deploy → contracts created | 1 day |
| Oracle adapter (Chainlink) | Price feed → Daml oracle contract | 1 day |
| Compliance gate (TRM) | AML check → Daml compliance gate | 1 day |
| Other adapters | Noves, ALUM, Chainalysis — monitoring, readable data, health | 1–2 days |
| Total |  | ~6–7 days |

## W12–16: Testing, Migration & Launch

| Task | Detail | Time |
| --- | --- | --- |
| Canton testnet E2E | Full flow: connect → discover → deploy → negotiate → settle $CC | 2 days |
| Load testing | 10+ concurrent deals, 50+ parties | 1 day |
| Security audit support | Work with IEU on Daml audit, third-party on API audit | Liz schedules |
| Dual-write soak test | 2 weeks running both. Monitor for drift. | 2 weeks |
| Cutover | CANTON_MODE=live. Daml = source of truth. PostgreSQL = cache. | 1 day |
| Staged rollout | Internal → 5 partners → all partners → public | 3 weeks |
| Total |  | ~3 weeks active + 2–3 weeks soak |

# Engineering Cost Summary

| Phase | Work | Calendar | Active Days | Cost @ $1.5K/day |
| --- | --- | --- | --- | --- |
| W1 | Onboarding portal | Week 1 | 3 days | $4,500 |
| W2 | Node configuration | Week 2 | 2 days | $3,000 |
| W3–4 | Identity verification | Weeks 3–4 | 6 days | $9,000 |
| W4–5 | LiveCanton scaffold | Weeks 4–5 | 3 days | $4,500 |
| W5–7 | Pre-build (waiting on IEU) | Weeks 5–7 | 8 days | $12,000 |
| W7–8 | LiveCanton live | Weeks 7–8 | 5 days | $7,500 |
| W9–10 | $CC settlement | Weeks 9–10 | 8 days | $12,000 |
| W10–11 | CPM + adapters | Weeks 10–11 | 7 days | $10,500 |
| W12–16 | Test + launch | Weeks 12–16 | 15 days | $22,500 |
| TOTAL |  | 16 weeks | 57 days | $85,500 |

# Total Program Cost

## Minimum Viable M3

Get it live with essential vendors only.

| Category | Cost |
| --- | --- |
| Will’s engineering | $85K–$115K |
| IEU (license + hosting + Daml contracts) | $200K–$280K |
| Fireblocks enterprise | $50K–$75K |
| Essential partner APIs (Chainlink + TRM) | $36K–$60K/year |
| Security audit | $25K–$35K |
| Minimum Year 1 Total | $395K–$565K |

## Full M3

All vendors, all partner APIs, complete ecosystem integration.

| Category | Cost |
| --- | --- |
| Will’s engineering | $85K–$115K |
| IEU (full engagement) | $250K–$370K |
| Fireblocks enterprise | $50K–$100K |
| All partner APIs | $72K–$192K/year |
| Security audits | $25K–$50K |
| 5North + 7Trust | TBD (partnership) |
| Full Year 1 Total | $480K–$825K |

## Year 2+ Recurring

| Category | Annual |
| --- | --- |
| IEU hosting + license | $122K–$220K |
| Fireblocks | $50K–$100K |
| Partner APIs | $36K–$192K |
| Will’s maintenance | ~$30K–$50K |
| Year 2+ Total | $240K–$560K |

# Decision Matrix for Liz

Priority call list, in order. Each call unblocks specific engineering work.

| # | Call | Ask | Impact if Delayed | Target |
| --- | --- | --- | --- | --- |
| 1 | Chris (IEU) | Confirm test node, sign partnership, commit Daml timeline | Everything stops | This week |
| 2 | Fireblocks | Start enterprise agreement, get sandbox access | $CC settlement delayed | This week |
| 3 | 5North | API access for Canton-native KYC | Verification badges delayed | Week 2 |
| 4 | 7Trust | API for Party-ID DNS verification | Same as above | Week 2 |
| 5 | TRM Labs | Compliance screening API for pre-trade checks | Compliance adapter delayed | Week 8 |
| 6 | Chainlink/Pyth | Price feed API for collateral valuation | Oracle adapter delayed | Week 8 |
| 7 | Security firm | Schedule Daml + API audit for Week 14 | Launch delayed | Week 10 |

# What Will Starts Monday

- Build the participant onboarding portal. No blockers. Ships this week. Liz can start inviting partners immediately.

- Write the exact Daml contract specification to hand to IEU — every template, every choice, every field. So when Liz gets IEU signed, the spec is ready and IEU can start immediately.

- Pre-build the Fireblocks client library against their public API docs — so when Liz gets sandbox access, Will swaps in real credentials and it works.

# Appendix: What’s Already Built (M2)

For Liz’s context when talking to vendors. We are not starting from zero.

| Already Delivered | Evidence |
| --- | --- |
| 57 API routes (auth, flows, deals, admin, billing) | Production code |
| 20+ database tables with full schema | Drizzle ORM, Neon PostgreSQL |
| 80+ Canton participant profiles | Static data + DB table ready |
| Canton service interface (5 methods) | Interface + mock + factory pattern |
| Deal state machine (5 states + transitions) | Working in PostgreSQL |
| Real-time messaging (SSE + polling) | Working in production |
| JWT auth with Canton Party-IDs | Working in production |
| Role-based access control (3 roles) | Enforced everywhere |
| File upload/storage | Vercel Blob integration |
| Audit logging | All actions logged |
| Test node running | canton.test.catalyst.flowryd.xyz — 126 endpoints |

M2 was explicitly designed for zero-frontend-change M3 upgrade. The mock→live swap is an engineering task, not a rewrite.

Built on $15K of delivered infrastructure. Engineering starts Monday.

William Lee  |  Full-Stack Engineer

Previous: Flowryd Control Centre M1 ($7,500) + M2 ($7,500) = $15,000 delivered